## Book6
RINGS
Objective | Time(Weeks) | Cost | Deliverables | Iteration
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 1
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 1
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 1
Concept Devlopment | 1 | 1 | 3D renderings, sketches, material choices, third party | 2
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 2
Customer feedback | 1 | 1 | Let customers use item, get feedback | 2
Concept Devlopment | 1 | 1 | 3D renderings, sketches, material choices, third party | 3
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 3
Customer feedback | 1 | 1 | Let customers use item, get feedback | 3
BANDS
Objective | Time(Weeks) | Cost | Deliverables | Iteration
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 1
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 1
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 1
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 2
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 2
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 2
Concept Devlopment | 1 | 1 | 3D renderings, sketches, material choices, third party | 3
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 3
Customer feedback | 1 | 1 | Let customers use item, get feedback | 3
SUSPENSION STRAPS
Objective | Time(Weeks) | Cost | Deliverables | Iteration
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 1
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 1
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 1
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 2
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 2
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 2
Concept Devlopment | 1 | 1 | 3D renderings, sketches, material choices, third party | 3
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 3
Customer feedback | 1 | 1 | Let customers use item, get feedback | 3
YOGA STRAPS
Objective | Time(Weeks) | Cost | Deliverables | Iteration
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 1
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 1
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 1
Concept Development | 1 | 1 | 3D renderings, sketches, material choices, third party | 2
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 2
Customer Feedback | 1 | 1 | Let customers use item, get feedback | 2
Concept Devlopment | 1 | 1 | 3D renderings, sketches, material choices, third party | 3
Prototype Signoff/Development | 2 | 2 | Green light prototypes to be developed, approve cost | 3
Customer feedback | 1 | 1 | Let customers use item, get feedback | 3